## Ringkasan
Finance Portal Odoo — Estimasi Mandays
Scope: Odoo-only · SAP & HC/HRIS = Out of Scope · 2026-07-01
Total Proyek (incl. PMO + Kontingensi 15%) |  | Total Non-PMO (dengan Kontingensi 15%) |  | Build Phase Non-PMO (tanpa Kontingensi)
462 |  | 408 |  | 202
Semua 7 fase · semua role |  | BA + Dev + QA · semua 7 fase |  | BA + Dev + QA · Fase Build saja
Rekap per Fase — Semua Role
No | Fase | PMO | BA | Dev | QA | Total | Keterangan
1 | Requirement & Analysis | 8 | 22 | 3 | 4 | 37 | FSD draft, kontrak integrasi final
2 | Design (FSD/TSD) | 3 | 8 | 10 | 6 | 27 | TSD, data model sign-off, mockup
3 | Build (lihat sheet Build Detail) | 18 | 35 | 123 | 44 | 220 | Sprint 2-mingguan → breakdown di sheet 'Build Detail (202)'
4 | SIT | 5 | 6 | 12 | 16 | 39 | E2E pass — gated: konektor SAP/Kafka/HRIS ready
5 | UAT | 5 | 12 | 12 | 8 | 37 | UAT sign-off user
6 | Cutover & Go-Live | 4 | 5 | 8 | 3 | 20 | Parallel run, cutover day
7 | Hypercare | 4 | 5 | 9 | 3 | 21 | Stabilisasi 3 minggu, handover support
| Subtotal (tanpa kontingensi) | 47 | 93 | 177 | 84 | 401
| + Kontingensi 15% | 7 | 14 | 27 | 13 | 61
| TOTAL (dengan kontingensi) | 54 | 107 | 204 | 97 | 462 | Grand total termasuk PMO
| Total Non-PMO = 462 − 54 | — | 107 | 204 | 97 | 408 | Angka ini setara spreadsheet klien (tanpa PMO)
Keterangan: PMO (54 md) dikeluarkan karena spreadsheet klien hanya mencantumkan kolom IT BA & IT Dev. Angka 202 = Fase Build saja (BA 35 + Dev 123 + QA 44). Angka 408 = semua 7 fase + kontingensi 15%, tanpa PMO.

## Semua Fase (408)
Estimasi Mandays — Semua Fase (Total Non-PMO = 408 md · incl. PMO = 462 md)
No | Fase / Aktivitas | BA | Dev | QA | Total | % dari total | Keterangan
1 | Requirement & Analysis | 22 | 3 | 4 | 29 | 9.2% | FSD draft, stakeholder interview, kontrak integrasi final
2 | Design (FSD/TSD) | 8 | 10 | 6 | 24 | 6.7% | TSD & data model sign-off, UI mockup, JSON payload spec
3 | Build / Development | 35 | 123 | 44 | 202 | 54.9% | Sprint 2-mingguan, feature complete → detail di sheet 'Build Detail (202)'
4 | SIT | 6 | 12 | 16 | 34 | 9.7% | Gated: konektor SAP/Kafka/HRIS ready; E2E pass
5 | UAT | 12 | 12 | 8 | 32 | 9.2% | UAT sign-off dari user
6 | Cutover & Go-Live | 5 | 8 | 3 | 16 | 5.0% | Data migration, parallel run, cutover day
7 | Hypercare | 5 | 9 | 3 | 17 | 5.2% | Stabilisasi 3 minggu, handover ke support
| Subtotal (tanpa kontingensi) | 93 | 177 | 84 | 354 | 100%
| + Kontingensi 15% | 14 | 27 | 13 | 54 | 15%
| TOTAL (dengan kontingensi) | 107 | 204 | 97 | 408 | 115%
Catatan: Angka di tabel ini adalah TOTAL PROYEK (semua 7 fase). Sheet 'Build Detail (202)' berisi breakdown per-fitur untuk Fase 3 saja. Fase 1-2-4-5-6-7 tidak di-breakdown per-fitur karena aktivitasnya berupa kegiatan (workshop, review, testing), bukan deliverable fitur.

## Build Detail (202)
Build Phase Detail — Finance Portal Odoo (BA 35 + Dev 123 + QA 44 = 202 mandays, tanpa PMO & kontingensi)
No | WS | Modul | Fitur / Menu | Sub-Fitur / Task Odoo | Komponen Odoo | Interfacing | Complexity | BA | Dev | QA | Total
A. Foundation & SSO | [7 empty] | 2 | 12 | 3 | 17
A.1 | A | Foundation | Multi-company base scaffold | Manifest, __init__, install check, base model mixin | custom_finance_portal | Internal | Low | 0 | 2 | 0.5 | 2.5
A.2 | A | Foundation | Keycloak SSO sisi Odoo | auth_oauth config, role mapping, tenant isolation, redirect URI | custom_finance_portal_sso | SSO/Keycloak | High | 1 | 6 | 1.5 | 8.5
A.3 | A | Foundation | Security groups & access rules | Groups per role (Submitter / Tax / Finance / Admin), record rules | custom_finance_portal | Internal | Low | 0.5 | 2 | 0.5 | 3
A.4 | A | Foundation | CI/CD & static validation | py_compile, XML/ACL lint, install smoke test script | DevOps | Internal | Low | 0 | 1 | 0 | 1
A.5 | A | Foundation | Vendor Portal SSO login | Vendor auth flow via auth_oauth, session management sisi Odoo | custom_finance_portal | SSO/Keycloak | Low | 0.5 | 1 | 0.5 | 2
B. Master Data & Sync | [7 empty] | 6 | 14 | 4 | 24
B.1 | B | Master Data | Submission Type | CRUD + seed data (CA, Expense, PD, Invoice) | custom_finance_portal | Internal | Low | 0.5 | 0.5 | 0 | 1
B.2 | B | Master Data | Invoice Routine Type | CRUD (Routine / Non-Routine) | custom_finance_portal | Internal | Low | 0.5 | 0.5 | 0 | 1
B.3 | B | Master Data | Invoice Type | CRUD (PO / Non-PO Non-Trade) | custom_finance_portal | Internal | Low | 0.5 | 0.5 | 0 | 1
B.4 | B | Master Data | Item Category | Odoo model + upsert idempoten dari SAP webhook | custom_finance_portal_sap | SAP-API | Low | 0.5 | 1.5 | 0.5 | 2.5
B.5 | B | Master Data | Item of Submission | Odoo model + upsert idempoten dari SAP webhook | custom_finance_portal_sap | SAP-API | Low | 0.5 | 1.5 | 0.5 | 2.5
B.6 | B | Master Data | Supplier / Vendor Master | Upsert res.partner dari SAP webhook, dedup by vendor code | custom_finance_portal_sap | SAP-API | Low | 0.5 | 1.5 | 0.5 | 2.5
B.7 | B | Master Data | COA (Chart of Accounts) | Upsert account.account (filter GL relevan) dari SAP | custom_finance_portal_sap | SAP-API | Low | 0.5 | 2 | 1 | 3.5
B.8 | B | Master Data | Cost Budget per Divisi | Model budget + upsert dari SAP | custom_finance_budget | SAP-API | Low | 0.5 | 2 | 0.5 | 3
B.9 | B | Master Data | Approval Matrix | Upsert approval matrix + mapping approver Odoo user | custom_finance_portal_sap | SAP-API | Low | 0.5 | 1.5 | 0.5 | 2.5
B.10 | B | Master Data | Finance Approval Matrix | CRUD local — mapping PIC Finance per vertical | custom_finance_portal | Internal | Low | 0.5 | 1 | 0.5 | 2
B.11 | B | Master Data | Vertical / Business Plant | Upsert dari SAP, linked ke res.company | custom_finance_portal_sap | SAP-API | Low | 0.5 | 0.5 | 0 | 1
B.12 | B | Master Data | User Master (sync SAP/HRIS) | Upsert res.users + cron job scheduler | custom_finance_portal_sap | SAP-API/HRIS | Low | 0 | 0.5 | 0 | 0.5
B.13 | B | Master Data | User Role (sync SAP) | Upsert res.groups mapping dari role SAP | custom_finance_portal_sap | SAP-API | Low | 0.5 | 0.5 | 0.5 | 1.5
C. Cash Advance + Realization | [7 empty] | 4 | 14 | 5 | 23
C.1 | C | Cash Advance | Request CA – List & Filter | List/kanban view, search panel, filter status/date/CA number | custom_finance_portal | Internal | Low | 0.5 | 1.5 | 0.5 | 2.5
C.2 | C | Cash Advance | Request CA – Create/Edit form | Form: CA No, PR/PO, requester, NIK, company, division, amount, tgl payment, metode, bank, rekening, penerima, approver, note | custom_finance_portal | Internal | High | 1 | 3 | 1 | 5
C.3 | C | Cash Advance | Validasi PR (> Rp 1jt wajib PR) | Constraint + lookup nomor PR dari SAP (real-time) | custom_finance_portal_sap | SAP-API | Low | 0.5 | 2 | 0.5 | 3
C.4 | C | Cash Advance | Approval workflow Tax→Finance | Approval engine 2 level: Tax Review → Finance Review | custom_finance_portal | Internal | Low | 0.5 | 1.5 | 0.5 | 2.5
C.5 | C | Cash Advance | Push CA ke SAP | Adapter: POST ke SAP endpoint, async via queue_job | custom_finance_portal_sap | SAP-API | Low | 0.5 | 2 | 0.5 | 3
C.6 | C | CA Realization | Realization CA – List & Filter | List view, filter by CA/status | custom_finance_portal | Internal | Low | 0 | 0.5 | 0.5 | 1
C.7 | C | CA Realization | Realization CA – Create/Edit form | Link ke CA asal, tabel detail realisasi, sisa budget, tgl realisasi | custom_finance_portal | Internal | Medium | 1 | 2 | 1 | 4
C.8 | C | CA Realization | Approval Realization Tax→Finance | Reuse approval engine (beda state machine) | custom_finance_portal | Internal | Low | 0 | 0.5 | 0.5 | 1
C.9 | C | CA Realization | Terima status payment dari SAP | Webhook handler: update state CA + notif user | custom_finance_portal_sap | SAP-API | Low | 0 | 1 | 0 | 1
D. Reimbursement & Expenses | [7 empty] | 3 | 9 | 4 | 16
D.1 | D | Reimbursement | List & Filter | List view, filter by status/type/date | custom_finance_portal | Internal | Low | 0 | 1.5 | 0.5 | 2
D.2 | D | Reimbursement | Create/Edit form | Form field expense/reimbursement + attachment | custom_finance_portal | Internal | High | 1 | 3 | 1 | 5
D.3 | D | Reimbursement | Validasi PR (> Rp 1jt) | Reuse constraint + SAP PR lookup dari C.3 | custom_finance_portal_sap | SAP-API | Low | 0.5 | 0.5 | 0.5 | 1.5
D.4 | D | Reimbursement | Approval workflow Tax→Finance | Reuse approval engine | custom_finance_portal | Internal | Low | 0.5 | 1 | 0.5 | 2
D.5 | D | Reimbursement | Push expense ke SAP | Adapter: POST ke SAP endpoint, async via queue_job | custom_finance_portal_sap | SAP-API | Low | 0.5 | 2 | 0.5 | 3
D.6 | D | Reimbursement | Terima status payment dari SAP | Webhook handler (reuse, beda state machine) | custom_finance_portal_sap | SAP-API | Low | 0.5 | 1 | 1 | 2.5
E. Vendor Invoice + Vendor Portal | [7 empty] | 4 | 18 | 6 | 28
E.1 | E | Invoice Non-PO | List & Filter | List view + filter status/date/vendor | custom_finance_portal | Internal | Low | 0 | 1.5 | 0.5 | 2
E.2 | E | Invoice Non-PO | Create/Edit form Non-PO | Form: nomor inv, GL Account, COA, attachment, approval | custom_finance_portal | Internal | High | 1 | 3 | 1 | 5
E.3 | E | Invoice Non-PO | Approval workflow Tax→Finance | Reuse approval engine | custom_finance_portal | Internal | Low | 0.5 | 1 | 0.5 | 2
E.4 | E | Invoice Non-PO | Push MIRO posting ke SAP | Adapter: POST invoice posting ke SAP, async queue_job | custom_finance_portal_sap | SAP-API | Low | 0.5 | 2 | 1 | 3.5
E.5 | E | Invoice PO | List & Filter PO-linked | List view + lookup PO/GR dari SAP | custom_finance_portal | SAP-API | Low | 0 | 1.5 | 0.5 | 2
E.6 | E | Invoice PO | Create form PO-linked | Auto-populate dari PO/GR SAP, validasi qty/nilai GR | custom_finance_portal_sap | SAP-API | High | 1 | 3 | 1 | 5
E.7 | E | Invoice PO | Approval workflow Tax→Finance | Reuse approval engine | custom_finance_portal | Internal | Low | 0 | 1 | 0.5 | 1.5
E.8 | E | Invoice PO | Push MIRO posting ke SAP (PO-linked) | Adapter (reuse E.4, beda payload PO-linked) | custom_finance_portal_sap | SAP-API | Low | 0.5 | 1.5 | 0.5 | 2.5
E.9 | E | Vendor Portal | Login Vendor (SSO) + landing | Vendor auth flow via auth_oauth, landing page submit invoice | custom_finance_portal | SSO/Keycloak | Low | 0.5 | 2 | 0.5 | 3
E.10 | E | Vendor Portal | Submit invoice + tracking status | Vendor-facing form + polling status dari SAP | custom_finance_portal_sap | SAP-API | Low | 0 | 1.5 | 0.5 | 2
F. Perjalanan Dinas | [7 empty] | 3 | 7 | 3 | 13
F.1 | F | PD Request | List & Filter | List view + filter by date/status | custom_finance_portal | HRIS-API | Low | 0 | 1 | 0.5 | 1.5
F.2 | F | PD Request | Create/Edit form | Form field sesuai kontrak HRIS: tujuan, tanggal, anggaran, tipe PD | custom_finance_portal | HRIS-API | Medium | 1 | 2 | 0.5 | 3.5
F.3 | F | PD Request | Approval workflow Tax→Finance | Reuse approval engine | custom_finance_portal | Internal | Low | 0.5 | 0.5 | 0 | 1
F.4 | F | PD Realization | List & Filter | List view | custom_finance_portal | Internal | Low | 0 | 1 | 0.5 | 1.5
F.5 | F | PD Realization | Create/Edit form Realization | Settlement: link ke PD asal, actual expense, lampiran bukti | custom_finance_portal | Internal | Low | 1 | 1.5 | 1 | 3.5
F.6 | F | PD Realization | Approval Realization | Reuse approval engine | custom_finance_portal | Internal | Low | 0.5 | 1 | 0.5 | 2
G. Budget Control | [7 empty] | 3 | 8 | 3 | 14
G.1 | G | Budget Control | Budget limit check per divisi | Computed field sisa budget pada form dokumen | custom_finance_budget | Internal | Low | 0.5 | 2 | 0.5 | 3
G.2 | G | Budget Control | Validasi & lookup PR (≥ Rp 1jt) | SAP PR lookup adapter + onchange constraint | custom_finance_portal_sap | SAP-API | Low | 0.5 | 2 | 0.5 | 3
G.3 | G | Budget Control | Lookup & validasi PO/GR | SAP PO/GR adapter + populate fields | custom_finance_portal_sap | SAP-API | Low | 0.5 | 2 | 0.5 | 3
G.4 | G | Budget Control | Remaining budget display (computed) | Computed field: budget − committed − realisasi | custom_finance_budget | Internal | Low | 0.5 | 1 | 0 | 1.5
G.5 | G | Budget Control | Alert + blocking rule over-budget | Warning popup + hard-block state constraint | custom_finance_budget | Internal | Low | 1 | 1 | 1.5 | 3.5
H. Integration Odoo-side | [7 empty] | 4 | 16 | 6 | 26
H.1 | H | Integration | Adapter base (REST caller + retry) | Base class HTTP REST, timeout, retry 3×, error mapping | custom_finance_portal_sap | SAP-API | High | 1 | 3 | 1 | 5
H.2 | H | Integration | Push job async via queue_job | CA, expense, MIRO push job + priority queue | custom_finance_portal_sap | Internal | Low | 0.5 | 3 | 1 | 4.5
H.3 | H | Integration | Webhook receiver + HMAC validator | HTTP controller endpoint, signature validation, dispatch handler | custom_finance_portal_sap | SAP-API | Low | 0.5 | 3 | 1 | 4.5
H.4 | H | Integration | Sync log menu | Tree/form view log (sukses/gagal/pending) per dokumen + retry button | custom_finance_portal_sap | Internal | Low | 0.5 | 3 | 1 | 4.5
H.5 | H | Integration | Master data upsert cron | ir.cron jobs untuk upsert harian semua master dari SAP | custom_finance_portal_sap | SAP-API | Low | 0.5 | 2 | 1 | 3.5
H.6 | H | Integration | Dead-letter retry + alert email | queue_job failure handler, email notif ke admin | custom_finance_portal_sap | Internal | Low | 1 | 2 | 1 | 4
I. Reporting + Dashboard | [7 empty] | 3 | 12 | 4 | 19
I.1 | I | Dashboard | Cash Advance Dashboard | Stat blocks (New/On Process/Reject/Pending) + filter date + search CA# | OWL/ir.ui.view | Internal | Low | 0.5 | 2 | 0.5 | 3
I.2 | I | Dashboard | Reimbursement Dashboard | Stat blocks + list mini | OWL/ir.ui.view | Internal | Low | 0 | 1 | 0 | 1
I.3 | I | Dashboard | Invoice Vendor Dashboard | Stat blocks (Non-PO & PO) + filter | OWL/ir.ui.view | Internal | Low | 0 | 1 | 0 | 1
I.4 | I | Dashboard | Perjalanan Dinas Dashboard | Stat blocks + list mini | OWL/ir.ui.view | Internal | Low | 0 | 1 | 0 | 1
I.5 | I | Reporting | Login log | Wrapper ir.logging + list view + filter user/date | custom_finance_portal | Internal | Low | 0.5 | 1 | 0.5 | 2
I.6 | I | Reporting | Transaction audit log | Audit trail model (create/update/approve/reject) + wizard export | custom_finance_portal | Internal | Low | 0.5 | 2 | 1 | 3.5
I.7 | I | Reporting | Cash Advance report (Excel/PDF) | QWeb report template + xlsx export | custom_finance_portal | Internal | Low | 0.5 | 1 | 0.5 | 2
I.8 | I | Reporting | Reimbursement report | QWeb report template + xlsx export | custom_finance_portal | Internal | Low | 0.5 | 1 | 0.5 | 2
I.9 | I | Reporting | Invoice Vendor report | QWeb report template + xlsx export | custom_finance_portal | Internal | Low | 0.5 | 1 | 0.5 | 2
I.10 | I | Reporting | Sync log report / export | List view + CSV export | custom_finance_portal_sap | Internal | Low | 0 | 1 | 0.5 | 1.5
J. Configuration | [7 empty] | 2 | 4 | 2 | 8
J.1 | J | Configuration | Finance Portal settings panel | ir.config_parameter + settings view (base URL SAP, secret token, flags) | custom_finance_portal | Internal | Low | 1 | 2 | 0.5 | 3.5
J.2 | J | Configuration | Limitation for Submission master | Model + CRUD view (limit per submission type/divisi) | custom_finance_portal | Internal | Low | 0.5 | 1 | 0.5 | 2
J.3 | J | Configuration | Sync config (endpoint, topic, token) | Settings form per integrasi + test-connection button | custom_finance_portal_sap | Internal | Low | 0.5 | 1 | 1 | 2.5
K. Non-Functional | [7 empty] | 1 | 9 | 4 | 14
K.1 | K | Non-Functional | PDP classification audit | Data category fields, access log, custom_pdp_classification reuse | custom_pdp_classification | Internal | Low | 0.5 | 2 | 1 | 3.5
K.2 | K | Non-Functional | Security hardening | SQL injection, XSS, IDOR review + perbaikan sisi Odoo | All modules | Internal | Low | 0 | 2 | 1 | 3
K.3 | K | Non-Functional | Performance (N+1 / prefetch) | Profiling query, prefetch_ids, pagination | All modules | Internal | Low | 0 | 2 | 1 | 3
K.4 | K | Non-Functional | Resilience (circuit breaker + timeout) | Adapter timeout, fallback state, exponential backoff | custom_finance_portal_sap | Internal | Low | 0.5 | 3 | 1 | 4.5
GRAND TOTAL FASE BUILD (tanpa PMO, tanpa kontingensi) | [7 empty] | 35 | 123 | 44 | 202
Rumus Kompleksitas
Complexity |  | BA | Dev | QA | Total/baris
Low |  | 0.5 | 1.5 | 0.5 | 2.5
Medium |  | 1 | 3 | 1 | 5
High |  | 2 | 5 | 2 | 9