## 1. Summary
Tenant Levi's (PT Era Busana Retailindo) — Data Review & Scope
Generated: Phase 1 review deliverable
Item | Keputusan / Status
Tenant DB | era_busana_retailindo
Legal entity | PT Era Busana Retailindo
App principal | XStore Levi's — saat ini one-way report; target FTP file integration
Store coverage | 1 toko (14694 / SAP 0020069514 / OLS SCU – TUNJUNGAN PLAZA 3), 1 register
Periode data sample | 26 Apr – 11 Mei 2026 (DRY-RUN, bukan go-live cutoff)
Modul Odoo aktif (proposal) | purchase, sale_management, account, l10n_id, l10n_id_efaktur, custom_coretax, custom_pdp_*
X24DN Retail Sales | Masuk Odoo via sale_management (SO/Invoice)
X31 Discount Journal | Detail promo per line dari X24DN; join via TRANSNUM
X20 Onhand + X32P Stock Movement | ABAIKAN untuk saat ini (GR/stock di-handle XStore)
X101 Material Master | Load semua 214,305 row → restruktur ke template + variant + attribute + pricelist
Customer master | Pakai 1 partner generic 'Walk-in Customer' (sampai klarifikasi member)
Tax | PPN 11/12 efektif 11%, gross include tax — konfirmasi: PMK 131 (custom_coretax) atau account.tax standar
Encoding | Pertahankan karakter ® di nama produk; sumber XLSX corrupt � perlu di-fix
Admin user | admin default, DB baru fresh
Pajakku ASPP | Konfirmasi: per-tenant credential atau shared platform
Currency precision IDR | PENDING konfirmasi user (default Odoo decimal=2)

## 2. X101 Material Master
X101_Material_Master.xlsx — 214,305 baris × 16 kolom
# | Kolom | Arti | Statistik / Catatan | Mapping Odoo (proposal)
1 | PRODUCT CODE | Kode model/template produk | 14,885 unique. Contoh: 0002E-0031 | product.template.default_code
2 | ITEM DESCRIPTION | Nama produk | Mengandung ® (sumber corrupt � perlu replace) | product.template.name
3 | BRAND | Brand | 1 distinct: LEVIS | Tidak digunakan (constant)
4 | CATEGORY | Top-level kategori | 6 distinct: MENS BOTTOMS (101,511), WOMENS BOTTOMS (50,576), MENS TOPS (32,488), WOMENS TOPS (20,511), MENS ACCESSORIES (5,530), MENS FOOTWEAR (2,143), WOMENS ACCESSORIES (1,546) | product.category lvl 1
5 | CLASS | Sub-kategori | Top: JEANS (131,341), TEES (24,174), WOVEN TOPS (16,088), KHAKIS (9,140), SHORTS (6,687) | product.category lvl 2
6 | SUBCLASS | Sub-sub kategori | TERPOTONG 10 char: REGULAR OR, LOOSE OR B, GRAPHIC TE, WOVEN SHIR, NON GRAPHI, MID LENGTH, BOOTCUT OR — butuh full text | product.category lvl 3
7 | PRICE LEVEL | Tier pricelist | 1 distinct: MARKET | Nama pricelist tunggal 'MARKET'
8 | LEVEL VALUE | Kode level (?) | 1 distinct: LVAMAID — arti? | Tidak digunakan (perlu konfirmasi)
9 | PROD SKU | SKU varian | 159,658 unique, 54,647 BARIS DUPLIKAT. Contoh: 0002E00310L | product.product.default_code
10 | ITEM SIZE | Size variant | Top: 32, 30, 31, 29, 28, 34, M, S, L, 33, 27, 36, XL | product.attribute 'Size' value
11 | INSEAM | Inseam (bottoms only) | 72,588 row = '-' (non-bottoms). Sisanya: 32, 30, 34, 29, 28, 36, 31, 33, 27 | product.attribute 'Inseam' value (skip '-')
12 | PROD GTIN | Barcode EAN-13 | 0 row kosong di dataset full | product.product.barcode (primary)
13 | PROD JAN | Barcode JAN Jepang | 57,667 kosong (OK, sekunder) | Optional / ignore
14 | ITEM RETAIL PRICE | Harga retail include PPN | Format INTEGER (749900 = Rp 749,900). Tidak ada PRICE per template berbeda (0 produk dengan >1 harga) | product.template.list_price
15 | PRICE EFFECTIVE FROM | Tanggal efektif harga | Datetime. Tidak ada PRICE EFFECTIVE TO → asumsi aktif sampai sekarang | product.pricelist.item.date_start

## 3. X24DN Retail Sales
X24DN_Retail_Sales_Detail_Report.xlsx — 945 data + 1 grand total × 59 kolom
# | Group | Kolom | Arti | Catatan / Mapping
1 | Store | STORE CODE | Kode toko numerik | 14694 (semua sama)
2 | Store | SAP STORE CODE | Kode toko SAP | 0020069514 — untuk mapping ke SAP/principal
3 | Store | STORE NAME | Nama toko | OLS SCU - TUNJUNGAN PLAZA 3
4 | Header | TRANS DATE | Tanggal transaksi | Date only
5 | Header | REGISTER | Nomor POS register | Selalu 1 (1 register)
6 | Header | TRANSNUM | Nomor transaksi | 330 unique transaksi di sample → KEY untuk grouping SO
7 | Reversal | ORIGINAL STORE CODE | Ref toko transaksi asli (jika void/return) | None di sample 945
8 | Reversal | ORIGINAL TRANS SEQ | Ref transnum asli | None di sample
9 | Reversal | ORIGINAL WKSTN ID | Ref workstation asli | None di sample
10 | Staff | STAFF ID | ID karyawan | Contoh: 14694001000119 (= store + suffix)
11 | Staff | STAFF NAME | Nama karyawan + emp.no | Contoh: '2125048 RANI LESTARI'
12 | Line | ITEM TYPE | Jenis line | Selalu PRODUCT
13 | Line | LINE ID | Urutan line di struk | Integer
14 | Line | ITEM CODE | SKU dari X101
15 | Variant | WAIST | Waist size | Untuk bottoms
16 | Variant | INSEAM | Inseam | Untuk bottoms
17 | Item | ITEM DESCRIPTION | Nama item | Konsisten dengan X101 (encoding ®)
18 | Item | BRAND | Brand | LEVIS
19 | Item | CATEGORY | Kategori | Sama X101
20 | Item | CLASS | Class | Sama X101
21 | Item | SUBCLASS | Subclass | Sama X101 (10-char truncate)
22 | Item | EAN CODE | Barcode
23 | Pricing | ITEM RETAIL PRICE | Harga retail listed | Sebelum discount
24 | Pricing | ITEM GROSS PRICE | Harga jual aktual (inc tax, post-discount)
25 | Pricing | NET SOLD QUANTITY | Qty terjual | Integer; negatif jika return
26 | Pricing | NET DISCOUNT AMOUNT | Discount per line
27 | Pricing | NET SOLD AMOUNT | Subtotal ex-tax
28 | Tax | TAX RATE | Tax rate | 0.11 (PPN 11%)
29 | Tax | TAX AMOUNT | Nilai PPN | Sample: 999900 inc → 99090 tax
30 | Tax | TOTAL AMOUNT | Total inc tax
31 | Discount 1 | DISCOUNT TYPE 1 | Tipe diskon slot 1 | SEMUA None di sample 945 — promo asli ada di X31
32 | Discount 1 | DISCOUNT CODE 1 | Kode diskon slot 1 | None
33 | Discount 1 | DISCOUNT DESCRIPTION 1 | Deskripsi slot 1 | None
34 | Discount 1 | DISCOUNT AMOUNT 1 | Nilai diskon slot 1 | None
35 | Discount 1 | DISCOUNT PERCENTAGE 1 | % diskon slot 1 | None
36 | Discount 2 | DISCOUNT TYPE/CODE/DESC/AMOUNT/PERCENTAGE 2 | Slot diskon kedua | Semua None di sample
37 | Discount 3 | DISCOUNT TYPE/CODE/DESC/AMOUNT/PERCENTAGE 3 | Slot diskon ketiga | Semua None
38 | Discount 4 | DISCOUNT TYPE/CODE/DESC/AMOUNT/PERCENTAGE 4 | Slot diskon keempat | Semua None
39 | Notes | LINE ITEM -COMMENTS | Komentar line | Beberapa berisi string ID seperti '012861-012860-012859'
40 | Notes | TRANSACTION NOTES | Catatan transaksi | Mostly null
41 | Notes | RACE | Etnis customer | Semua null — field untuk pasar lain?
42 | Notes | SURVEY CUSTOMER TH | Survey field (TH = Thailand?) | Null — bisa di-ignore di ID
43 | Notes | TYPE OF SALE TH | Type of sale (TH = Thailand?) | Null — bisa di-ignore
44 | Member | ALTERNATE ID/MEMBER ID | ID member loyalty | Contoh: 6281259849001 (phone number-like)
45 | Member | MEMBER TYPE | Tipe member | STAMPS_ID di 892 row, None di 53 (walk-in)
46 | Member | TELEPHONE NUMBER | No HP customer | Sama dengan member ID di sample (PDP masking required)
47 | Member | Omni Order Id | Reference omni-channel order | None di sample

## 4. X31 Discount Journal
X31_Discount_Journal.xlsx — 33 data rows × 25 kolom (header di row 8)
Periode: 26 Apr – 11 Mei 2026 ¦ Promo unique: 4 kode (LPAID1117 CRM-VIP, PPA Telkomsel, LPAID1706 Birthday, LPAID2307 Retention)
# | Kolom | Arti | Catatan
1 | STORE CODE | Kode toko | 14694
2 | SAP STORE CODE | SAP store | 0020069514
3 | STORE NAME | Nama toko | OLS SCU - TP3
4 | TRANSNUM | Nomor transaksi | KUNCI JOIN ke X24DN.TRANSNUM
5 | TRANS DATE | Tanggal
6 | TRANS TIME | Jam transaksi | HH:MM:SS
7 | DISCOUNT ID | ID promo | Contoh: LPAID1117, 14323:104721:PPA:TR150
8 | DISCOUNT CODE | Kode promo | Kadang sama dengan DISCOUNT ID, kadang beda — semantics perlu klarifikasi
9 | DISCOUNT DESCRIPTION | Deskripsi promo | Contoh: 'CRM-VIP DISCOUNT', 'ID-PPA-Telkomsel Redemption V150K-Feb-May 2026'
10 | BRAND | Brand | LEVIS
11 | CATEGORY | Kategori | Sama X101
12 | CLASS | Class | Sama X101
13 | SUBCLASS | Subclass | Sama X101
14 | PRODUCT CODE | Kode template
15 | ITEM DESCRIPTION | Nama item | Konsisten X101
16 | PRODUCT SCANNED | Barcode di-scan
17 | WAIST | Waist | Untuk bottoms
18 | INSEAM | Inseam | Untuk bottoms
19 | NET SOLD QUANTITY | Qty di-discount | Integer
20 | ITEM GROSS PRICE | Harga gross sebelum promo X31 | Inc tax
21 | NET SOLD AMOUNT | Harga setelah discount | Inc tax
22 | DISCOUNT AMOUNT | Nilai potongan
23 | PERCENT DISCOUNT | % potongan | String dengan spasi prefix, contoh ' 29.55'
24 | NOTE | Catatan staff | Contoh: STAFF ID '14694001000127'
25 | STAFF ID + timestamp | Kolom 24-25? | Sample tampilkan staff name '2123110 RYMA NURGHAIDA' + datetime — kemungkinan 2 kolom terpisah

## 5. X20 & X32P (Skipped)
X20 Onhand Inventory + X32P Stock Movement — SKIPPED untuk dry-run
Alasan: GR & inventory di-handle XStore (app principal). File ini hanya reference.
X20_Current_Onhand_Inventory_Report.csv
Kolom | Arti | Catatan
STORE CODE / SAP STORE CODE / STORE NAME | Identitas toko | 14694 / 0020069514 / OLS SCU TP3
ITEM ID | SKU
WAIST / INSEAM | Variant
ITEM DESCRIPTION / EAN / BRAND / CATEGORY / CLASS / SUBCLASS | Item info | Konsisten X101
BIN | Lokasi rak di toko | Contoh: EXT_STORAGE
ONHAND QTY | Stok saat snapshot | Integer
(Catatan format CSV) | Format aneh | Double-header (textbox* + business header tumpuk) — minta XStore re-export bersih
X32P_Stock_Movement_Report_With_Price.xlsx
Kolom | Arti | Catatan
STORE CODE / SAP STORE CODE / STORE NAME | Toko
PRODUCT CODE | Template
WAIST / INSEAM | Variant
ITEM DESCRIPTION / BRAND / CATEGORY / CLASS / SUB CLASS | Item info
OPENING ONHAND / OPENING ONHAND RETAIL | Stok awal periode (qty + nilai retail)
INVENTORY ADJUSTMENT / ADJUSTMENT RETAIL | Penyesuaian stok
ITEM SALE / SALES RETAIL | Qty terjual + nilai retail
POSTVOID ITEM SALE (×2) | Kolom duplikat! | Kolom 19 kemungkinan = POSTVOID SALES RETAIL (typo header)
ITEM RETURN / RETURN RETAIL | Qty return + nilai
POSTVOID ITEM RETURN / POSTVOID RETURN RETAIL | Postvoid return
RECEIVING / RECEIVING RETAIL | Penerimaan barang
RECEIVING VOID / RECEIVING VOID RETAIL | Void receiving
SHIPPING / SHIPPING RETAIL | Pengiriman
SHIPPING VOID / SHIPPING VOID RETAIL | Void shipping
ITEM TRANSFER / ITEM TRANSFER RETAIL | Transfer antar toko
TOTAL QTY MOVED | Total pergerakan
ENDING ONHAND / ENDING ONHAND RETAIL | Stok akhir periode

## 6. Data Statistics
Statistik temuan dari Phase 1 exploration
File | Metrik | Nilai
X101 Material Master | Total rows | 214,305
X101 Material Master | Unique PRODUCT CODE (template) | 14,885
X101 Material Master | Unique PROD SKU (variant) | 159,658
X101 Material Master | Baris duplikat PROD SKU | 54,647 (PERLU KLARIFIKASI strategi dedup)
X101 Material Master | Empty PROD GTIN | 0
X101 Material Master | Empty PROD JAN | 57,667 (OK, sekunder)
X101 Material Master | Distinct BRAND | 1 (LEVIS)
X101 Material Master | Distinct PRICE LEVEL | 1 (MARKET)
X101 Material Master | Distinct LEVEL VALUE | 1 (LVAMAID)
X101 Material Master | Distinct CATEGORY | 6 (MENS/WOMENS × BOTTOMS/TOPS/ACCESSORIES + MENS FOOTWEAR)
X101 Material Master | Distinct INSEAM '-' (non-bottoms) | 72,588
X101 Material Master | Product dengan >1 distinct price | 0 (harga stabil per template)
X24DN Retail Sales | Total line rows | 945 (+ 1 Grand Total)
X24DN Retail Sales | Unique transactions | 330
X24DN Retail Sales | Unique stores | 1 (14694)
X24DN Retail Sales | Unique registers | 1
X24DN Retail Sales | Lines dengan MEMBER_TYPE=STAMPS_ID | 892
X24DN Retail Sales | Lines tanpa member (walk-in) | 53
X24DN Retail Sales | TAX RATE | 0.11 (PPN 11%)
X31 Discount Journal | Total data rows | 33
X31 Discount Journal | Distinct discount codes | 4
X31 Discount Journal | → LPAID1117 CRM-VIP DISCOUNT | 21 rows
X31 Discount Journal | → 14323:104721:PPA:TR150 Telkomsel Redemption V150K | 7 rows
X31 Discount Journal | → LPAID1706 CRM-Birthday Voucher | 2 rows
X31 Discount Journal | → LPAID2307 CRM-Retention V200K-OLS | 1 row
X32P Stock Movement | Total rows | 14,971 (di-skip untuk dry-run)
Periode | Start - End | 26 Apr 2026 – 11 Mei 2026 (16 hari, sample dry-run)

## 7. Clarifications Required
Daftar klarifikasi yang harus dijawab user / principal Levi's / Tax consultant
Kolom 'Answer' kosong untuk diisi oleh stakeholder. Prioritas High = blocking untuk migration plan final.
# | Kategori | Topik | Pertanyaan | Priority | Blocking? | Owner | Answer
1 | C.1 X101 | Dedup strategy | 54,647 baris duplikat PROD SKU — apa artinya? Strategi dedup: ambil row terbaru per PROD SKU by PRICE EFFECTIVE FROM, atau ada makna bisnis lain? | High | Yes | User / XStore
2 | C.1 X101 | SUBCLASS terpotong | SUBCLASS terpotong 10 char (REGULAR OR, LOOSE OR B, GRAPHIC TE, ...). Bisa re-export dengan full text, atau supply mapping table manual? | High | Yes | Principal Levi's
3 | C.1 X101 | PRODUCT CODE pattern | PRODUCT CODE (0002E-0031) = style code Levi's global authoritative untuk template? PROD SKU = PRODUCT_CODE + SIZE + INSEAM? | Med | No | Principal Levi's
4 | C.1 X101 | Barcode fallback | Untuk SKU tanpa PROD GTIN (0 di full dataset, tapi safety): generate internal barcode dari PROD SKU, kosongkan, atau skip SKU? | Low | No | User
5 | C.1 X101 | Variant matrix | Produk JEANS punya 2 axis WAIST × INSEAM. Generate semua kombinasi (matrix) atau hanya yang muncul di file? | Med | No | User
6 | C.1 X101 | Pricelist effective end | Semua harga aktif sampai sekarang? Atau perlu price history multiple item dengan date_start naik? | Med | No | User
7 | C.1 X101 | LEVEL VALUE arti | LEVEL VALUE = LVAMAID — singkatan apa? Confirm bisa di-ignore. | Low | No | Principal Levi's
8 | C.1 X101 | IDR currency precision | Decimal places untuk IDR di company config Odoo: 0 atau 2? Default Odoo IDR = 2. Confirm. | High | Yes | User
9 | C.2 X24DN | Formula reconcile | Confirm formula: GROSS × QTY = TOTAL; NET SOLD = TOTAL - TAX; NET DISCOUNT = RETAIL - GROSS per qty? | Med | No | User / XStore
10 | C.2 X24DN | Posting strategy SO | Per TRANSNUM = 1 sale.order multi-line? Atau aggregate harian per store? | Med | No | User
11 | C.2 X24DN | Payment method | Tidak ada kolom payment di X24DN. Pakai 1 default 'POS Cash' sampai data tersedia? Atau ada file payment terpisah? | High | Yes | User / XStore
12 | C.2 X24DN | Staff representation | STAFF ID → hr.employee, res.users, atau analytic tag di SO? | Med | No | User
13 | C.2 X24DN | Omni Order Id | Reference order e-commerce/app? Selalu None di sample — confirm. | Low | No | Principal Levi's
14 | C.2 X24DN | Member ID handling | Customer master nantinya di-push dari CRM Stamps loyalty, atau Odoo simpan member ID sebagai metadata tanpa partner? | Med | No | User
15 | C.2 X24DN | Reversal/void flow | Kolom ORIGINAL STORE/TRANS SEQ untuk return/postvoid (None di sample). Untuk go-live: handle dengan credit note? | Low | No | User
16 | C.2 X24DN | Field TH suffix | RACE, SURVEY CUSTOMER TH, TYPE OF SALE TH — TH = Thailand? Bisa ignore di Indonesia? | Low | No | Principal Levi's
17 | C.3 X31 | Join key 1:1 | Apakah (TRANSNUM, PRODUCT CODE, WAIST, INSEAM) cukup unik untuk join 1:1 ke X24DN line? | Med | No | User / XStore
18 | C.3 X31 | Stacked promo | X24DN punya 4 slot discount (None semua), X31 row per promo. Bisa 1 line punya ≥2 promo (stacked)? | Med | No | User
19 | C.3 X31 | DISCOUNT ID vs CODE | Perbedaan DISCOUNT ID vs DISCOUNT CODE? Untuk LPAID1117 sama, untuk PPA Telkomsel beda. Semantics? | Med | No | Principal Levi's
20 | C.3 X31 | Discount accounting | Discount: (a) line di SO/invoice kurang revenue, (b) journal terpisah ke 'Promotion Expense' + receivable ke principal? Berbeda per CRM vs PPA Telkomsel (co-op reimburse)? | High | Yes | User / Tax consultant
21 | C.3 X31 | Kolom 24-25 X31 | Sample tampilkan staff name + datetime — confirm 2 kolom terpisah? | Low | No | XStore
22 | C.4 Tax | PMK 131 vs standar | Levi's wajib e-Faktur Pajakku? Pakai custom_coretax PMK 131 fiscal position atau cukup account.tax standar? | High | Yes | Tax consultant
23 | C.4 Tax | PPN 11/12 formula | Formula tax base = gross/1.11 atau gross × (11/12)/1.10? Rounding policy? Sample: 999,900/1.11 = 900,810.81 → file tampil 900,810 + 99,090. | High | Yes | Tax consultant
24 | C.4 Tax | Revenue split | Sales journal: revenue 1 akun tunggal atau pecah per CATEGORY/CLASS via analytic? | High | Yes | User / Accountant
25 | C.4 Tax | Cash account | POS sales: akun bank/cash/e-wallet/QRIS — apa saja perlu disiapkan? | High | Yes | User / Accountant
26 | C.4 Tax | COA template | Pakai l10n_id standar atau custom Levi's retail COA? Jika custom, supply file COA. | High | Yes | User / Accountant
27 | C.5 Tenant | Modul list final | Confirm install: purchase, sale_management, account, l10n_id, l10n_id_efaktur, custom_coretax. Skip: stock, point_of_sale. custom_pdp_* yang mana (audit, masking, classification)? custom_hub_console? | High | Yes | User
28 | C.5 Tenant | Multi-store readiness | Saat ini 1 store. Siapkan struktur branch (l10n_id branch) atau warehouse dari awal? Atau analytic account? | Med | No | User
29 | C.5 Tenant | FTP integration roadmap | Tahap 2: FTP drop folder + Odoo cron pickup. Skema folder & jadwal? | Low | No | User / Principal
30 | C.5 Tenant | Vendor PO awal | Vendor lokal pertama yang harus dibuat? (Levi Strauss Indonesia? Supplier lokal?) Belum ada file vendor master. | High | Yes | User
31 | C.5 Tenant | Pajakku ASPP | Credential per-tenant atau shared platform? Untuk e-Faktur Levi's perlu NPWP + sertifikat digital sendiri. | High | Yes | User / Tax consultant
32 | C.5 Tenant | Company master data | NPWP 16 digit, alamat, sertifikat e-Faktur, KLU, KPP terdaftar PT Era Busana Retailindo — belum tersedia. | High | Yes | User
33 | C.6 Quality | Encoding chars lain | Sumber XLSX corrupt � di tempat ®. Confirm tidak ada karakter lain yang corrupt (™, é, ñ, dll)? | Med | No | User / XStore
34 | C.6 Quality | X32P kolom duplikat | POSTVOID ITEM SALE muncul 2× di header X32P. Kolom 19 kemungkinan POSTVOID SALES RETAIL. Confirm (non-blocking selama X32P di-skip). | Low | No | XStore
35 | C.6 Quality | X20 CSV re-export | Minta XStore re-export X20 dengan format clean (single header, UTF-8). Non-blocking. | Low | No | XStore
36 | C.6 Quality | Grand Total row X24DN | Baris terakhir X24DN = Grand Total → skip saat parse (sudah noted, internal handling). | Low | No | Internal

## 8. Tenant Config Proposal
Tenant: era_busana_retailindo (PT Era Busana Retailindo) — Module install proposal
Module | Install? | Alasan | Status / Catatan
base, web | YES | Core Odoo | Auto-install
purchase | YES | Scope user: PO untuk vendor lokal | Confirm vendor list awal (C.5 #30)
sale_management | YES | Sales POS dari XStore masuk Odoo sebagai SO/Invoice | Confirmed
account | YES | Scope user: FICO | Confirmed
l10n_id | YES | Localization Indonesia (COA, taxes) | Confirm COA standard atau custom (C.4 #26)
l10n_id_efaktur | YES | e-Faktur Pajakku output | Perlu sertifikat & credential (C.5 #31)
custom_coretax | TBD | PMK 131 fiscal positions & PPN 11/12 policy | Confirm dengan tax consultant (C.4 #22)
custom_pdp_masking | YES | Mask PII customer (member ID = phone) | Wajib untuk compliance UU PDP
custom_pdp_audit | YES | Audit log akses data sensitif | Wajib
custom_pdp_classification | TBD | Klasifikasi data PII | Confirm scope (C.5 #27)
custom_hub_console | TBD | Admin tenant UI | Confirm jika user butuh self-admin (C.5 #27)
stock | NO | GR & inventory di-handle XStore | Skip — kecuali nanti FICO butuh valuasi
point_of_sale | NO | POS native Odoo tidak dipakai (XStore yg POS) | Skip
mrp, project, hr, website, mass_mailing | NO | Out of scope | Skip

## 9. Migration File List
File / folder yang akan dibuat saat eksekusi migration (BELUM DIBUAT)
Path | Tujuan | Sumber data
addons/_tenants/era_busana_retailindo/__manifest__.py | Tenant module manifest | Manual
addons/_tenants/era_busana_retailindo/__init__.py | Module init | Manual
addons/_tenants/era_busana_retailindo/data/res_company.xml | Company master (NPWP, alamat, sertifikat) | C.5 #32
addons/_tenants/era_busana_retailindo/data/res_partner_walkin.xml | Generic walk-in customer | Hardcode
addons/_tenants/era_busana_retailindo/data/res_partner_vendors.xml | Vendor lokal awal | C.5 #30
addons/_tenants/era_busana_retailindo/data/product_category.xml | Category 3-level (CATEGORY/CLASS/SUBCLASS) | X101 dedup distinct
addons/_tenants/era_busana_retailindo/data/product_attribute.xml | Attribute Size + Inseam + values | X101 distinct
addons/_tenants/era_busana_retailindo/data/product_template.csv | 14,885 template | X101 grouped by PRODUCT CODE
addons/_tenants/era_busana_retailindo/data/product_product.csv | 159,658 variant | X101 dedup by PROD SKU
addons/_tenants/era_busana_retailindo/data/product_pricelist.xml | Pricelist MARKET | X101
addons/_tenants/era_busana_retailindo/data/account_tax_setup.xml | PPN 11/12 setup (jika tidak via custom_coretax) | C.4 #22-23
scripts/tenants/era_busana_retailindo/import_x101.py | ETL X101 → product master | X101 file
scripts/tenants/era_busana_retailindo/import_x24dn_x31.py | ETL Sales + Discount per TRANSNUM | X24DN + X31
scripts/tenants/era_busana_retailindo/reconcile.py | Validasi total revenue & tax | Sales journal vs file
docker-compose.multitenant.yml (edit) | Register tenant DB | Add 'era_busana_retailindo' to LIST_DB
odoo/odoo.conf.tmpl (verify) | dbfilter route | Sudah handle multi-tenant

## 10. Verification Plan
Post-migration verification checklist
# | Test | Expected Result | Status
1 | Tenant DB provision | DB 'era_busana_retailindo' ada di Postgres, dbfilter route → instance Odoo public | [ ]
2 | Module install | `-i purchase,sale_management,account,l10n_id,l10n_id_efaktur,custom_coretax,custom_pdp_masking,custom_pdp_audit --stop-after-init` exit 0 | [ ]
3 | Product master dry-run (100 SKU) | 100 template/variant ter-load, attribute Size/Inseam ter-generate benar | [ ]
4 | Product master full | 159,658 SKU (post-dedup) ter-load tanpa error, total < 15 menit | [ ]
5 | Sales dry-run X24DN | 330 SO created dari 945 line; PPN 11% reconcile (sample 999,900 inc → 900,810 base + 99,090 tax) | [ ]
6 | Discount dry-run X31 | 33 promo lines ter-apply ke SO line yang benar (via TRANSNUM); accounting sesuai keputusan C.3 #20 | [ ]
7 | FICO reconcile | Total revenue + total PPN di Odoo sales journal == total file X24DN | [ ]
8 | PDP masking | Member ID & phone customer ter-mask sesuai role | [ ]
9 | PDP audit log | Akses data PII ter-log di custom_pdp_audit | [ ]
10 | e-Faktur output | Sample 1 invoice di-export ke format Pajakku, validasi XSD | [ ]